## Sheet1
Phil Weinstein, July 2014 Activity Report, edit 8-1-2014 (a)
Bugs (not related to ongoing new development)
| 1 | 5519 CLOSED -- TableSeries Slot Dlg: selection stats not working
| 1.5 | 5495 Followup: Plot Periodic Slot Dlg: Remove Time Range settings
| 2.5 | 5510: Crash modifying a plot page config via the output manager
| 3.75 | 5513: SCT: "Interpolate Between Inputs" wasn't always working.
| 7.25 | 5517: Can't import Table Slot exported with new DMI export meta-data
… Note: 5517 could potentially be reported as TVA 6 followup (Dec/Jan): Assist Migration to PMF model
… See last item (#7): http://cadswes2.colorado.edu/~philw/2013/Opt/LimitTableCheck/Bake1.html
| 1 | 5522: Empty user Subbasins were dropped on model load.
| 1 | General Bug Research
18 | 18 | Total
Other Maintenance Work
| 2.5 | RiverWare 6.5 Release documentation support
| 0.5 | Support Tool analysis (Java application on Maelstrom).
3 | 3 | total
Misc (unfunded) software and documentation enhancements
| 1.25 | FIX: Diagnostics filter statistics visibility bug.
| 1 | Diag Context "Open" Operation: more specific item-type description
2.25 | 2.25 | total
Funded Development Tasks
BOR Truckee
| 7.5 | Analysis and Project Management
| 18.25 | SCT: Show Slot Descriptions in, and from the SCT
… http://cadswes2.colorado.edu/~philw/2014/BorTruckee/ShowSlotDesc/project.html
| 27.75 | Plot Print Preview and Margin Settings
... http://cadswes2.colorado.edu/~philw/2014/PlotPrintPreview/project.html
| 2 | FIX to Printing Plots: User Configurable Headers and Footers.
| 17 | Teacup diagram and Output Visualization
… http://cadswes2.colorado.edu/~philw/2014/TeaCup/project.html
BOR IDIQ 11 -- LC Usability Enhancements
| 8.5 | Object Attributes analysis and design
BPA Adapter Release 1
| 17.5 | Ctrl/Exec Output DMI option: Limit Output to Run Range
TVA [#9] Minor SCT Enhancements
… http://cadswes2.colorado.edu/~philw/2014/TVA/July/project.html
| 8.75 | Webinar Meeting (7-16), Analysis and Project Management
| 2.5 | SCT "Enter Navigation" Change for Horizontal Time Views
| 26 | SCT Import Paste Enhancements and Fixes
| 3 | Entered value didn't set Input flag if new value matches old [5521]
| 9.75 | Navigate Open SCTs to Diagnostic Message Context Slot and Timestep.
TVA [#11] New expression slots and triggers
| 5 | SCT: Expression Slot Update Trigger, design and estimate
… http://cadswes2.colorado.edu/~philw/2014/TVA/FEWS/SctExprSlotUpdateTrig.html
153.5 | 153.5 | total (Funded Development Tasks)
User Support
0 | 0
Professional Activities
0 | 0
RiverWare Commercial Activities
CC Payment and Web Page Support
| 0.75 | Online payment system item configuration
0.75 | 0.75 | total
General Project/Center Activities
| 7.25 | Software Team Meetings and discussions (7-2, 7-8, 7-14, 7-21, 7-28)
| 1 | June 2014 Activity Report
| 1.75 | June 2014 Accomplishments Report
| 1 | June 2014 Maintenance Report Compilation
| 3.5 | Annual Review, preparation and meeting
| 0.75 | Attended Rebecca Smith's defense (7-11)
| 2 | General Task Review
| 0 | Development System Maintenance
| 1 | GIT system maintenance
| 1 | Office organization
19.25 | 19.25 | total
Leave
| 0 | vacation (6 days)
| 0 | sick
0 | 0 | total
196.75 |  | Grand Total (for 21 work days)