## Sheet1
Phil Weinstein, June 2014 Activity Report, edit 7-2-2014 (a)
Bugs (not related to ongoing new development)
| 0.25 | 3718 CLOSED -- Crash changing model timestep: daily to monthly
| 3.25 | 4252 CLOSED -- Purify errors, memory leaks
| 0.25 | 5284 CLOSED -- Workspace File->Reopen Model menu selection ignored
| 0.25 | 5497 CLOSED -- (dup of 5490): Canceling drag-move 1st Rule in Group
| 4 | 4178: Obscure model corruption issues related to subbasins.
| 4.75 | 5487: Plot Dlg: assert fail after plotting single-column table slot
| 22 | 5495: Periodic slots are not repeated in graphs.
| 6 | 5500: Parametric Plot axis config problem when switching plots
| 3 | 5502: FilterByObjType (RPL func): only 1st type used; 'DataObj' prob.
| 4 | 5505: Diag window closes when invalid RPL set is loaded (sometimes)
| 5.75 | 5503: RPL: core dump using OBJ expression as TableSlot col index
| 7 | Research: TVA Slow Input DMI/SCT performance (see also 5506)
| 2 | 5506: Redundant DMI execution (GUI only)
| 2.25 | 5507: Creating subbasin from AggObjs selected on WS: Elem inclusion.
| 2 | 5510 (analysis): Crash modifying a plot page config via output mgr
66.75 | 66.75 | Total
Other Maintenance Work
| 2.25 | Regression Test Maintenance
| 3 | Support Tool analysis (Java application on Maelstrom).
5.25 | 5.25 | total
Misc (unfunded) software and documentation enhancements
| 1 | Minor RPL Palette Slot Name Selector usability enhancement
| 6 | RiverWare 6.5 Release Preparation
| 3 | Research addition of ListSlot to DataObjects.
10 | 10 | total
Funded Development Tasks
BOR IDIQ 10 -- RiverSMART enhancements
| 5 | Event Plugin Config class implementation, revisions
BOR IDIQ 11 -- LC Usability Enhancements
| 9 | Object Attributes analysis and design
TVA [#3] status meetings and estimates for future work
| 8.25 | TVA RW-FEWS integration SOW / Analysis of SCT req. and tasks
| 4.5 | SCT Expression Slot Update Trigger, analsis.
26.75 | 26.75 | total
User Support
0 | 0
Professional Activities
0 | 0
RiverWare Commercial Activities
CC Payment and Web Page Support
| 0.5 | Online payment system item configuration
0.5 | 0.5 | total
General Project/Center Activities
| 4.75 | Software Team Meetings and discussions (6-2, 6-9, 6-17)
| 2 | May 2014 Activity Report
| 3 | May 2014 Accomplishments Report
| 0.75 | June 2014 Activity Report (preliminary, before leaving for vacation)
| 1.5 | April 2014 Maintenance Report Compilation
| 5.5 | General Task Review
| 1.25 | Development System Maintenance
| 0.25 | Spring 2014 EPERs
| 3.25 | Attended DHI Presentation of Mike Customized (6-5)
22.25 | 22.25 | total
Leave
| 48 | vacation (6 days)
| 0 | sick
48 | 48 | total
179.5 |  | Grand Total (for 21 work days)