## Sheet1
Phil Weinstein, January 2015 Activity Report, edit 02-02-2014 (a)
Bugs (not related to ongoing new development)
| 31.5 | Gnats 5511: Plot DateTime on Y-axis
| 2.5 | Gnats 5523: Incr precision in ruleset and editing reverts to 8 digits
| 1.25 | Gnats 5532: Opt Sol Analysis Tool (POSAT) doesn't raise if already opened.
| 2 | Gnats 5548: DSS dataset file selector incorrectly queries replace file.
| 4 | Gnats 5575/5581: Right clicking in an SCT series cell can crash
| 5 | Gnats 5577: Tabular Series Slot Report: Monthly Timestep in Daily Model.
| 11.75 | Gnats 5580: SCT 'Init Rules' Tooltip and Context Menu Problems.
58 | 58 | Total
Other Maintenance Tasks
| 5.5 | Investigation: "Enable Rules Model Run Analysis" Checkbox.
5.5 | 5.5 | Total
Misc (unfunded) software and documentation enhancements
| 5.5 | rwSettings enhancement: apply 'enum' combo box changes immediately
… this enhancement fixed Gnats 5476.
| 14 | Plot Page Symbolic Time Range, and Change to config state
… mechanism: Design and Discussions
19.5 | 19.5 | total
Funded Development Tasks
TVA 10: "Preschedule SCT Enhancements"
| 28.75 | SCT: Automatic RPL slot evaluation on other series slot changes
| 19.25 | Custom Summary Rows: Hiding Individual Cells
USACE-ABQ, 6. Graphical Teacup and Animation for Links Output Device
| 4 | Fix to rwScript rwSetting seriaization problem caused by this new development
| 0.5 | Project assessment, analysis of time spent
USACE-ABQ, 7. [Data Object] Table Slot Operations
| 7 | Several avail col ops were not being shown (e.g. Insert Column) [5578]
| 13 | Reorder table slot columns
72.5 | 72.5 | total (Funded Development Tasks)
User Support
0 | 0
Professional Activities
0 | 0
RiverWare Commercial Activities
CC Payment and Web Page Support
| 0.5 | Payment system: item configuration
0.5 | 0.5 | total
General Project/Center Activities
| 1.75 | Software Team Meetings (1-26)
| 1 | Dec 2014 Activity Report
| 1 | Dec 2014 Accomplishments Report
| 0.25 | DEPA submission ("no conflict reported")
| 0.5 | General Task Review
| 1 | Release 6.6.1 support
| 1.5 | Sponsor Meeting Preparation
7 | 7 | total
Leave
| 0 | vacation
0 | 0 | total
163 |  | Grand Total (for 19 work days)