## Sheet1
Phil Weinstein, February 2015 Activity Report, edit 03-02-2015 (a)
Bugs (not related to ongoing new development)
| 8.5 | Gnats 5582: Huge delay operating Model Run Analysis dialog's Rules Effects panel with large Ruleset.
| 1 | Gnats 5583: Object Attribute Manager dialog: Missing button icons.
| 3 | Gnats 5584: Open Account Dialog and SCTs opened from an SCT file are not initially scrolled to the global time.
| 14.25 | Gnats 5587: Open Slot dialog: undesirable rescroll to selected cells after display change operations.
| 1 | Gnats 5591: On the Open Object dialog, the input I flag icon was not updating when the timestep changed.
| 1.25 | Gnats 5594: The SCT could jump to a different tab when removing a slot.
| 1.25 | General bug research and minor fixes
30.25 | 30.25 | Total
Other Maintenance Tasks
| 7.25 | Removed unnecessary options to disable two RPL analysis/performace measurement features.
| 1.25 | Qt4 to Qt5 port research [See 2-13-2015 e-mail].
8.5 | 8.5 | Total
Misc (unfunded) software and documentation enhancements
0 | 0 | total
Funded Development Tasks
TVA 10: "Preschedule SCT Enhancements"
| 10.5 | SCT: Custom Summary Rows: Fix and Usability Improvement
BOR-ABQ [_______] Graphical Teacup / Animated Flow Lines
| 21.5 | Flow Lines / SimObj Icons: project planning and documentation
| 58.5 | Flow Lines / SimObj Icons: development
BOR-ABQ [_______] Display RPL Predefined Function Help in RiverWare
| 8 | Development (just getting started, after work from 10 mos. ago).
98.5 | 98.5 | total (Funded Development Tasks)
User Support
0 | 0
Professional Activities
0 | 0
RiverWare Commercial Activities
CC Payment and Web Page Support
| 0.25 | website edit, remove class announcement (date passed).
0.25 | 0.25 | total
General Project/Center Activities
| 1.5 | Software Team Meetings (2-09).
| 13 | 2015 RiverWare User Group Meeting (2-03 and 2-04).
| 3 | 2015 Sponsor Meeting Preparation (incl. group meeting)
| 7.5 | 2015 Sponsor Meeting Attendance (2-05).
| 1.5 | Jan. 2015 Activity Report
| 3.25 | Jan. 2015 Accomplishments Report
| 0.5 | CADSWES Jan. 2015 Maintenance Accomp Compilation
| 1 | General Task Review
31.25 | 31.25 | total
Leave
| 0 | vacation
0 | 0 | total
168.75 |  | Grand Total (for 20 work days)