## Sheet1
Phil Weinstein, October 2015 Activity Report, edit 10-30-2015 (a)
Bugs (not related to ongoing new development)
| 0 | 5681: Model Reports: heading text always bold, even when 'normal'
… font style specified. (See Truckee Model Report Tasks).
| 3.75 | 5683: FlowLine slot names change when any SimObj renamed or created.
| 3.25 | 5684: New RPL objects use default precision (8 digits) instead of
… RPL Set's precision
7 | 7 | Total
Other Maintenance: Unfunded Development
| 4.5 | Qwt 5.2 to 6.1 port reasearch (10-1)
| 59.25 | Qwt 5.2 to 6.1 port development
| 10.5 | Plot Appearance Improvement Research (10-23)
| 44.25 | RiverWare source changes for Qt5 Port
118.5 | 118.5 | total
Funded Development Tasks
Truckee/USBR Model Report Tasks
| 3.75 | (Gnats 5681): Model Report: Normal/Bold section header text
| 1.75 | Added Level 5 Font Configuration
| 3.75 | Added ability to expand and contract Table of Contents section
Truckee/USBR Slot Usability
| 23.25 | Slot Dlg Display Prefs: Sel Stats, Notes Col, Slot Descript.
TVA / RTI Plotting Requirements
| 9 | Estimate: Plotting Feature Analysis and Estimates.
41.5 | 41.5 | total (Funded Development Tasks)
User Support
0 | 0 | total (User Support)
Professional Activities
0 | 0
RiverWare Commercial Activities
CC Payment and Web Page Support
| 1 | online payment item configurations, and maintenance issues.
1 | 1 | total
General Project/Center Activities
| 0 | Software Team Meeting.
| 0 | Sept 2015 Activity Report (done in Sept)
| 1 | Oct. 2015 Activity Report (this report)
| 1.25 | Sept. 2015 Accomplishments Report
| 0.75 | CADSWES Sept. 2015 Maintenance Accomp Compilation
| 20 | FY 2015 Annual Mantenance Report
| 0.5 | General Task Review
23.5 | 23.5 | total
Leave
| 0 | Vacation
191.5 |  | Grand Total (for 22 work days)