## Sheet1
Phil Weinstein, Jan 2017 Activity Report, edit 02-01-2017 (a)
Bugs (not related to ongoing new development)
*** FIXED BUGS ***
| 2.5 | 5871: SCT pre-run divider is incorrect when run aborts.
| 10.5 | 5877: SCT display issues when cutting (removing) a slot.
| 3.5 | 5880: Printed SCT has extra partial rows printed
| 3 | 5884/5856: Qt5 Port: phantom column remains after deleting column
| 0.75 | 5890: Right click in empty Model Report layout causes crash.
| 5.5 | 5891: Deleting column on custom table slot loses column labels
| 2.5 | 5900: RiverWare shifts marker X-position back 1 day when editing
| 5 | 5902: Plot Pages created in Output Manager not saved in model file
| 10 | 5903: Scripts, Set Table Slot Value Script Action not
correctly setting values with DateTime unit type.
*** Some work was done on these bugs (analysis, filed, assisted) ***
| 3 | 5901: Marker Label does not display unless a Line Style is selected
| 0.5 | General Bug Review
46.75 | 46.75 | Total
Other Maintenance / Unfunded Development / Maintenance Reporting
| 6.75 | SCT Default Font Simplification (RW 7.1)
… R:\doc\sct\2017\Fonts\SctDefaultFontRedesign-Jan2017.docx
| 3.5 | Reduced size of generated image files for model reports, video gen
| 4 | Oct/Nov/Dec 2016 CADSWES Maintenance Compilations
| 10.25 | FY 2016 Annual CADSWES Maintenance Report (Completed)
24.5 | 24.5 | total
Funded Development Tasks
COE ABQ Task 5.4: Rich Text Editing
… R:\doc\Output\ModelReport\2017\CoeAbq54-RichText-Features.docx
| 8 | (a) Super/Subscripting, (b) Tabs (insert non-breaking spaces)
COE ABQ Task 5.5: Show RPL Assignments in Model Report
… R:\doc\Output\ModelReport\2017\CoeAbq55-RplStmt-ModelReportItem.docx
| 31.5 | Model Report Item for Top-Level RPL Statements
COE ABQ Task 5.6: Script Groups (Willard's project)
| 1.5 | Assisting Willard with development issues.
COE SWD Task 5 Model Report Editor Features
… R:\doc\Output\ModelReport\2017\CoeSwd5-ModelReportEnhance-71-Features.docx
| 8.5 | (c): Embed images within HTML file.
| 18 | (d,e): Last Run information model report item
| 5.5 | (f): Show Desc/Comments checkboxes on various model report items
| 3 | project management and documentation
Truckee 1.7: Model Run History Data
| 6.25 | Retain Model Run History; Show in Model Info dialog (in progress)
82.25 | 82.25 | total (Funded Development Tasks)
User Support
0 | 0 | total (User Support)
Professional Activities
0 | 0
RiverWare Commercial Activities
CC Payment and Web Page Support
| 1 | online payment item configurations
1 | 1 | total
General Project/Center Activities
| 5.5 | Software Meetings (1-4, 1-24) and other software discussions.
| 2 | Dec 2016 Activity Report
| 2 | Dec 2016 Accomplishments Report
| 0.25 | Filed annual DEPA report ("no conflicts") (1-20)
9.75 | 9.75 | total
Work Total
164.25 |  | total (18 work days)
Leave
| 16 | Vacation (1-12 and 1-13)
| 0 | Sick / Medical Leave
16 | 16 | Leave Total
180.25 |  | Grand Total (for 20 work days)