## Sheet1
Phil Weinstein, Feb 2017 Activity Report, edit 3-01-2017, minor text edit 3-03-2017.
Bugs (not related to ongoing new development)
*** FIXED BUGS ***
| 5 | 5878: Time AggSerSlot unit col label incorrect after config change
| 1 | 5902 (followup): Plot Pages created in the Output Manager not saved.
| 3 | 5905: AggSeries Slot Add/Remove Column Operations Missing.
| 4.5 | 5908: After switching sheet, SCT scroll pos sometimes out-of-synch.
| 3 | 5991: SCT Sheets: 'Go To' doesn't always scroll to correct location.
16.5 | 16.5 | Total
Other Maintenance / Unfunded Development / Maintenance Reporting
| 3.75 | Build system maintenance
| 1.25 | January Maintenance Report Compilation
| 1 | E-mail system migration
6 | 6 | total
Funded Development Tasks
COE SWD Task 6: User Axis-Unit Configuration
… R:\doc\plotting\2017\CoeSwd6-UserPlotAxisUnits.docx
| 44 | development and documentation
COE SWD Task 9: Edit Multiple Plots and Curves within a Plot Page
| 58 | development, in progress.
Truckee 1.7: Model Run History Data
| 13.5 | Retain Model Run History; Show in Model Info dialog.
COE ABQ 5.6: Script Groups [Willard]
| 1.5 | development analysis and assistance
COE ABQ 5.9: Add action to change run timestep [Willard]
| 4.5 | development analyis and assistance.
[Robynn] "Go To" Next NaN
| 0.5 | development analysis
[Robynn] Output Canvas and Chart Enhancement Tasks / incl. Animation
| 2 | development analysis
124 | 124 | total (Funded Development Tasks)
User Support
0 | 0 | total (User Support)
Professional Activities
0 | 0
RiverWare Commercial Activities
CC Payment and Web Page Support
| 0.25 | online payment item configurations
0.25 | 0.25 | total
Sponsor Meeting (2-16-2017)
| 6 | Preparation and Followup
| 8 | Meeting
14 | 14 | total
General Project/Center Activities
| 6.5 | Software Meetings (2-7, 2-14) and other software discussions.
| 2 | Jan 2017 Activity Report
| 2.5 | Jan 2017 Accomplishments Report
11 | 11 | total
Work Total
171.75 |  | total (20 work days)
Leave
| 0 | Vacation
| 0 | Sick / Medical Leave
0 | 0 | Leave Total
171.75 |  | Grand Total (for 20 work days)