## Sheet1
Phil Weinstein, October 2017 Activity Report, edit 11-01-2017 (a)
Bugs (not related to ongoing new development)
*** FIXED BUGS ***
| 3.5 | 5735: Typing value into Edit Account dialog reports errors.
| 0.25 | 5984 (closed): Run Abort doesn't appear aborted run started w/Init
| 7 | 5988: Deleting link to multislot with slot open fails assertion.
| (*) | 6006: Object Viewer and Open Slot Issues (see below).
| 1.25 | 6020/6021: Plot crashes involving deleted objects.
| (**) | 6024: Issues with Water Balance (see below).
| 2 | 6025: Add Text and Add Image dialogs open on the upper left corner.
| 0.75 | General Bug Review
14.75 | 14.75 | Total
Other Maintenance / Unfunded Development / Maintenance Reporting
| 44.5 | Remove Slot Dialog Creation and Management from Open Obj Dlgs
(*) ... this was pursued in response to a part of Gnats 6006.
| 24.25 | Maintain Mass Balance Summary slot references through name changes.
(**) .. this was pursued in response to Gnats 6024.
| 1.5 | Monthly Maintenance Accomp Compilations (Jul, Aug, Sep 2017)
| 29 | FY2017 Maintanance Report
99.25 | 99.25 | total
Funded Development Tasks
USBR UC 1A: Software Enhancements
| 1.5 | Slot Viewer, minor fixes to September work.
USACE ABQ: Notes on Accounts (Improvements)
| 3 | Finishing: Enh. "Add/Paste Note" for Acct MultiSlot: Supply Option
USBR Truckee LBAO 1.2: Sum Flow to Volume
| 6 | Analysis
| 7.25 | Development (about 60% done)
USBR ABQ 3: Complete RiverWare Scenario Explorer for stakeholder use.
| 7 | Fixing object geometry problem in WsViewerWidget (in progress).
USACE ABQ 7: Show Output Canvas items on Workspace Views
| 3 | [Robynn] development assist and code review.
27.75 | 27.75 | total (Funded Development Tasks)
User Support
0
0 | 0 | total (User Support)
Professional Activities
0 | 0
RiverWare Commercial Activities
CC Payment and Web Page Support
| 0.25 | online payment item configurations.
0.25 | 0.25 | total
General Project/Center Activities
| 2.5 | Software Meeting (10-11), and various minor discussions
| 0.5 | General task research
| 1.5 | Sep 2017 Accomplishments Report
| 1 | Oct 2017 Activity Report (initial draft of this report)
5.5 | 5.5 | total
Work Total
147.5 |  | total
Leave
| 32 | Vacation: Oct 12, 13, 16, 30
| 0 | Sick / Medical Leave
32 | 32 | Leave Total
179.5 |  | Grand Total (for 22 work days)